## Schedule
Update Nature | Week Number | Delivery Date | Chapter Name | Chapter Number | Additional Details
1st Bi-weekly Update | 3 | 2023-06-22 | Demand | 1.1. | Complete
|  |  | Demand | 1.2.1. | Complete
|  |  | Supply | 1.5. | Partial
|  |  | Pricing | 2.2 | Partial (Excluding Price Forecasting)
Interim Report | 5 | 2023-07-06 | Demand | 1.2.2. | Partial (Only Volume)
|  |  |  | 1.2.3. | Complete
|  |  |  | 1.2.4. | Complete
|  |  |  | 1.2.5. | Complete
|  |  | Supply | 1.4.1. | Complete
2nd Bi-weekly Update | 7 | 2023-07-20 | Demand | 1.2.2. | Complete (With Monetary Sizing)
|  |  | Supply | 1.3. | Complete
|  |  |  | 1.4.2. | Complete
|  |  |  | 1.4.3. | Partial
|  |  |  | 1.5. | Complete
|  |  | Pricing | 2.2 | Complete (With Price Forecasting)
|  |  |  | 2.3. | Complete
|  |  |  | 2.4. | Complete
|  |  |  | 2.5. | Complete
|  |  | Competitive Analysis | 3.2. | Partial
3rd Bi-weekly Update | 9 | 2023-08-03 | Supply | 1.4.3. | Complete
|  |  | Pricing | 2.1. | Complete
|  |  |  | 2.6. | Complete
|  |  |  | 2.7. | Complete
|  |  | Competitive Analysis | 3.1. | Partial
|  |  |  | 3.2. | Compelete
|  |  | Sales And Logistic Strategy Analysis Of The Project | 4.1. | Partial
|  |  |  | 4.2. | Partial
Final Report | 10 | 2023-08-11 | Competitive Analysis | 3.1. | Complete
|  |  | Sales And Logistic Strategy Analysis Of The Project | 4.1. | Complete
|  |  |  | 4.2. | Complete
|  |  | Any Other Remaining Section |  | Complete
Note: Deliverable Format : Excel, PDF (as per requirement)
Note: There is a possibility of deviation in the deliverables schedule